## E-Digital Pakistan
E-Digital Pakistan - Planning & Monitoring - Work Plan
| Project Start Date | 2024-01-20 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18
| Project Lead | Muhammad Arif | [6 empty] | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12 | [6 empty] | 2024-02-19 | [6 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13
 | time axis 2024-01-15 to 2024-05-19
S.NO | TASK | Responsible | PREDECESSOR | START | Closing date | DAYS | % DONE | WORK DAYS | time axis 2024-01-15 to 2024-05-19
| Main Tasks/Sub Activities |  |  |  | - |  |  | -
0 | Setup and promote the organization structure at the National and Provincial level in Pakistan for liaison with Govt; department/authorities, private and humanitarian sectors representatives.
0.1 | Last three years audit report | sarbaz |  | 2024-01-22 | 2024-01-26 | 5 | 100% | 5
0.2 | ISO certification 9001-2015 Quality management - docs | Arif |  | 2024-01-29 | 2024-02-02 | 5 | 0% | 5
0.4 | update website/blog | Arif |  | 2023-12-13 | 2023-12-15 | 3 | 0% | 3
0.5 | E-Diigital Pakistan strategy 2022-2025 |  |  |  | - |  |  | -
0.6 | change of director E-Digital Pakistan |  |  |  | - |  |  | -
0.7 | KAPRA and Sales Tax registration | Arif |  | 2024-01-22 | 2024-01-26 | 5 | 100% | 5
0.8 | Registration with TVET |  |  |  | - |  |  | -
0.9 | acquire copy of contract from KPITB | Arif |  | 2024-01-22 | 2024-01-26 | 5 | 0% | 5
0.1 | apply for national membership |  |  |  | - |  |  | -
0.11 | apply for international membership |  |  |  | - |  |  | -
0.12 | Develop E-Digital Pakistan profile/brochure | Arif |  | 2024-01-22 | 2024-01-26 | 5 | 0% | 5
0.13 | application processed at sam.gov for UEI
1 | E-Digital NIC Project |  |  |  | - |  |  | -
1.1 | virtual/Physical meeting with DALP Team - at SWAT NIC | Arif |  | 2024-01-22 | 2024-01-26 | 5 | 0% | 5
[5 empty] | - |  |  | -
2 | Apply for funds/grants | [6 empty] | -
2.1 | follow up on IOM small grant |  |  |  | - |  |  | -
[5 empty] | - |  |  | -
[5 empty] | - |  |  | -
3 | Develop digital literacy skills of citizens to get maximum benefit of e-services, while maintaining safety. | [6 empty] | -
[5 empty] | - |  |  | -
[5 empty] | - |  |  | -
[5 empty] | - |  |  | -
4 | Create awareness and promote the e-services through social media, events, and meetings. | [6 empty] | -
4.1 | Develop digi directory listing available e-services |  |  |  | - |  |  | -
[5 empty] | - |  |  | -
[5 empty] | - |  |  | -
5 | Develop Digi Skills of youth, startups to build the digital workforce for development of eservices through modern technology | [6 empty] | -
[5 empty] | - |  |  | -
[5 empty] | - |  |  | -
[5 empty] | - |  |  | -
6 | Building capacity of the Public, Private and Humanitarian sectors in eservice delivery internally within department, organizations and to the citizens. | [6 empty] | -
[5 empty] | - |  |  | -
[5 empty] | - |  |  | -
[5 empty] | - |  |  | -
[5 empty] | - |  |  | -
Note on B13: Muhammad Arif: https://mranti.my/ https://www.buildingchangetrust.org/ FOSI - for digital parenting https://www.internetmatters.org/

## List of Partners-Stakeholders
S.No | Name | Company | Contact No | Email id

## Checklist
E-Digital Pakistan Checklist for grantseeking/readiness
CHECKLIST
This checklist shows E-Digital Pakistan readiness before applying for grant funding.
Activity | Yes/No | Need Action | Completion date
Partnering with another organization as a subcontractor can be an excellent strategy for building financial sustainability.
whether your organization is ready to start competing for a specific grant award opportunity.
the USDA SBIR program funds early or “seed” stage research and development that has commercial potential. The program provides equity-free funding and entrepreneurial support at the earliest stages of company and technology development.

## Grant Funding Plan E-Digital
Funding Plan E-Digital Pakistan
most recent modification date:
Program, service or activity | Funding source | Address, Telephone, Email, and Website: |  |  | Contact Person/Title: | Request: funds required | Application Deadline/Giving Cycle: | Assigned To: | Status/Results:
|  | Telephone | Email | Website
skills training partners | NAVTAC | 919217663 |  | https://nsis.navtcc.gov.pk |  |  | 5th October | Arif | The online apply will start from 20th September, 2023

## Grant Tracking sheet
Tracking potential funders application
S.No | Funder Name | Anticipated idea | ARC/EDP | Website | Call status (Open/Closed) | Deadline | Average range of funding | Antiicipated notification date | Date submitted | Status | Outcomes | Approved
1 | CIPE | Request for Proposals: Protecting Internet Freedom and Digital Rights |  | https://www.cipe.org/who-we-are/opportunities/request-for-proposals-protecting-internet-freedom-and-digital-rights/ | closed | 31st Dec - 2023 | USD $10,000
2 | Palladium | Digital Accelerated Learning Pathways |  | http://letsmakeitpossible.com/palladium-challenge-fund/ | closed | 27th October 2023 | up to AUS100.000 |  | 26th October, 2023 | acknowledgement received - committee in progress | Not accepted | No
3 | Karandaz | digital payments |  | https://karandaaz.com.pk/our-programs/karandaaz-digital/national-payments-infrastructures/raast-moe/ | closed | 17th November 2023 |  | 31st Oct - proposal development workshop |  | dateline was 27th Nov- time over | not submitted | No
4 | innovation fund | EU | EDP | https://climate.ec.europa.eu/eu-action/eu-funding-climate-action/innovation-fund/calls-proposals_en | open |  |  |  |  | Both calls will open on 23 November 2023 (tentative).
5 | IOM | business plan for 5 million grant | EDP |  | open |  | 5 million |  | 9th January, updated application submitted | physical assessment conducted on 20th Nov
6 |  | The Liveability Challenge 2024 Submission Form |  | https://www.theliveabilitychallenge.org/participate | open | Deadline: 09 February 2024, 23:59 (GMT +8)
7 | Bill & malinda gates foundation | Childcare and women development |  | https://gcgh.grandchallenges.org/challenge/strengthening-childcare-models-advance-womens-economic-power | closed | 6th December, 2023 | $400,000 USD |  |  | missed the deadline - |  | No
8 | Japan embassy |  |  | https://www.pk.emb-japan.go.jp/JapanPakistanRelations/GrantAssistance-new.html | open |  |  |  |  | open all the time
9 | WWF | small grants |  | https://www.wwfpak.org/take_action/small_grants_programme/ | open |  |  |  |  | open all the time
10 | TB REACH Wave 11 | STOP TB |  | https://www.stoptb.org/waves-of-funding/wave-11 | closed | January 17, 2024. |  | Final funding decisions will be made in June 2024.
11 | reach52 | partnership |  | https://reach52.com/growth-partners/ | closed | December 31, 2023 |  |  |  | applied
12 | IDRC | Education and Science Knowledge and Innovation Exchange Program |  | https://idrc-crdi.ca/en/funding/kix-call-proposals-knowledge-and-innovation-supporting-teacher-professional-development | closed | January 15, 2024 - 23:59 | CAD500,000
13 | Climate & Clean Air Coaltion | Pakistan - Advancing Implementation of Pakistan’s National Clean Air Policy Through Clean Cooking Fuels and Technologies [PK-23-003] |  | https://www.ccacoalition.org/calls-for-proposals/2023-calls-proposals-projects-advance-national-policy-and-mitigation-actions/pakistan-advancing-implementation-pakistans-national-clean-air-policy-through-clean-cooking-fuels-and-technologies-pk-23-003 | closed | 2024-01-07 | US$ 240,000 - US$ 300,000
14 | Durshal | seed funding | EDP |  | open | 29th January , 2024 | 3 million
15 | IMSciences | digital skills manuals development and training of 600 participants | EDP |  | open | 30th January, 2024 | 6 million
16
17